## Project Charter
PROJECT CHARTER — Conversational AI (Phase 1)
One-page scope summary. Blue = you fill in · Green = pulled from the ROI Forecast tab (don't overwrite).
PROJECT IDENTITY
Project name | Order-Cancellation Assistant
Business sponsor
Conv AI BA / Architect | Denis Šuško
Date / Version
SCOPE
Primary goal | Automate order cancellation (~15% of inbound chat volume).
Target channel(s) | Webchat widget
In-scope intents | check_order_status, cancel_order
Out of scope | Voicebot / telephony; issuing monetary refunds directly (bot cancels order state only — refund handled by finance).
Authentication | Logged-in webchat session token; unauthenticated users routed to login before any account action.
Handoff triggers | Order value > €500; OR 2 consecutive failed inputs; OR negative sentiment.
BUSINESS CASE (Phase 1 — auto-pulled from ROI Forecast)
Monthly contacts resolved by bot
Agent hours freed / month
Estimated savings / month (€)
Estimated savings / year (€)
SUCCESS CRITERIA (agree targets + baselines during scoping)
Resolution rate — target vs. current baseline
Escalation rate — acceptable ceiling
CSAT — bot vs. agent
Repeat-contact rate within 7 days (guards against fake containment)
ASSUMPTIONS · DEPENDENCIES · RISKS
Assumptions | Order-management REST API available in test; historical chat logs exportable; owner can sign off tone & guardrails.
Dependencies | Identity/SSO team (auth); contact-centre platform (live handover); Legal/DPO (GDPR sign-off); works council (Betriebsrat) alignment + Betriebsvereinbarung where the bot touches employee workflows (DACH).
Risks | Legacy systems without APIs cap automation; poor-quality logs weaken NLU; over-optimistic resolution targets erode trust; in DACH, starting build before works-council sign-off can freeze the project.

## How to Use
Conversational AI — Phase 1 (Scoping) Templates
Three linked tables that turn raw contact-centre data into a funded Phase-1 roadmap. Fill them left to right: Discovery (facts) → Feasibility (judgment) → ROI (money).
WORKFLOW — fill the tabs in this order
Tab 1 · Channel Discovery | WHAT customers contact you about today, and how much it costs. Observed data collected BEFORE any bot is built — from call/chat logs, ticket analytics, support managers.
Tab 2 · Feasibility Matrix | CAN the bot actually do it? For each intent you judge API readiness, complexity, and a realistic Target Resolution %. Where BA/architect expertise sets the phase plan.
Tab 3 · ROI Forecast | WHAT it's worth. Pulls volume from Tab 1 and resolution % from Tab 2 automatically, applies one editable agent-cost rate, and outputs monthly + annual savings.
COLOR KEY
Blue text | You type this in (raw data / your judgment).
Yellow cell | Key assumption to set once — the agent cost rate on Tab 3. Everything recalculates from it.
Green text | Pulled automatically from another tab. Don't overwrite — it will break the link.
Black text | Calculated for you. Don't overwrite.
KEY DEFINITIONS (so stakeholders agree on terms)
Intent | The AI's internal code-name for one thing the customer wants (e.g. cancel_order). "Stop my shipment", "cancel order 1001", "I bought the wrong item" = different words, one intent.
Monthly Volume | Historical demand from EXISTING channels (phone, live chat, email, tickets) — how many times humans handle this today. NOT hoped-for bot chats.
Target Resolution % | Share of that intent's contacts the bot completes end-to-end, with NO human. Base the money model on this — not on "containment".
Resolution ≠ Containment | Containment = the session never reached a human (includes people who gave up and re-contact you later). Resolution = the task was actually completed. This pack uses Resolution.
Why never 100%? | Business rules block it (order shipped, value > threshold), user input fails (can't find Order ID), sentiment escalates ("give me a human!"), or the backend API errors out.
Sessions ≠ Intent volume | One chat can trigger several intents ("where's my order?" then "cancel it"). Count intents, not sessions, when sizing volume.

## 1. Channel Discovery
TABLE 1 — Existing Channel Discovery (Raw Contact-Centre Data)
Collected BEFORE building anything, from call/chat logs, ticket analytics and support managers. Blue cells = you fill in. Sample rows are an example — replace with your client's data.
Contact Driver / Goal | Mapped Intent Name | Existing Channels Used | Monthly Volume | Avg Handle Time (min) | Notes
Track delivery progress | check_order_status | Phone, Webchat, Email | 20000 | 3 | Top contact driver
Cancel pending order | cancel_order | Phone, Webchat | 7500 | 5 | Guardrail: value > €500 needs manager
Change shipping address | change_address | Email, Web forms | 10000 | 8 | Legacy mainframe, no API

## 2. Feasibility Matrix
TABLE 2 — Technical Prioritization & Feasibility Matrix
Filled by the Conv AI BA / architect. Target Resolution % = share of that intent's contacts the bot completes end-to-end with no human (see How to Use). Blue cells = you fill in.
Intent Name | API Readiness | Complexity | Target Resolution % | Recommended Priority | Rationale (why this %)
check_order_status | High (REST API exists) | Low | 70% | Phase 1 (Quick Win) | User gives Order ID, bot queries API, returns tracking. ~30% drop out: typos, unauthenticated accounts, lost packages.
cancel_order | High (REST API exists) | Medium | 40% | Phase 1 (Quick Win) | Many attempts fail auto-completion: order already shipped, exceeds €500, or needs manager override.
change_address | Low (Legacy mainframe) | High | 10% | Phase 2 (Backlog) | No API → FAQ / deflection only. Cannot automate the write action.

## 3. ROI Forecast
TABLE 3 — Phase-1 ROI Forecast
Money math for the executive business case. Volume pulls from Table 1, Resolution % from Table 2 — automatically. Only edit: the yellow rate + which intents (column A) you include in Phase 1.
ASSUMPTIONS
Blended agent cost (€ / hour) | 50
Cost per minute (€)
Replace €50 with your client's fully-loaded agent cost (salary + overhead). Every figure below recalculates from it.
Intent Name (Phase 1) | Monthly Volume | AHT (min) | Target Resolution % | Monthly Resolved | Saved Agent Hours / mo | Monthly Savings (€) | Annual Savings (€)
check_order_status
cancel_order
TOTALS
Executive takeaway (auto-updates): read the TOTALS row into a sentence — "By automating these Phase-1 intents we resolve the Monthly Resolved figure with no human help, saving the Monthly Savings figure per month and freeing the Saved Agent Hours for higher-value work."